## Sheet1
Activity |  | Responsible | Estimated Duration (Weeks) | Earliest |  | Latest |  | Total Slack
|  |  |  | Start | Finish | Start | Finish
1 | Research React Native Frameworks and Libraries | Ziyaad | 5 | 0 | 5 | 12 | 17 | 12
2 | Configure the development environment | Keval | 2 | 5 | 7 | 17 | 19 | 12
3 | Platform documentation | Kreason | 2 | 5 | 7 | 18 | 20 | 13
4 | Database Entities | Kreason | 5 | 5 | 10 | 20 | 25 | 15
5 | Define API endpoints | Ziyaad | 9 | 5 | 14 | 19 | 28 | 14
6 | Set up core navigation dependancies | Ziyaad | 2 | 7 | 9 | 19 | 21 | 12
7 | Implement React Native navigation stacks | Keval | 6 | 9 | 15 | 21 | 27 | 12
8 | Create sample form state validation logic for reports | Kreason | 2 | 15 | 17 | 35 | 37 | 20
9 | Integrate device camera API | Keval | 5 | 15 | 20 | 29 | 34 | 14
10 | React Native geolocation | Ziyaad | 4 | 15 | 19 | 27 | 31 | 12
11 | Automatic device time capture | Kreason | 3 | 15 | 18 | 31 | 34 | 16
12 | Develop image preview screen | Ziyaad | 2 | 20 | 22 | 34 | 36 | 14
13 | Integrate an image compression library | Kreason | 1 | 22 | 23 | 36 | 37 | 14
14 | Runtime permission prompts | Kreason | 4 | 19 | 23 | 31 | 35 | 12
15 | Automatic Location tracking | Keval | 2 | 23 | 25 | 35 | 37 | 12
16 | Embed timestamp in metadata | Keval | 2 | 18 | 20 | 34 | 36 | 16
17 | Timestamp display | Ziyaad | 1 | 20 | 21 | 36 | 37 | 16
18 | Error Handling | Kreason | 2 | 25 | 27 | 37 | 39 | 12
19 | Create Wireframes | Ziyaad | 4 | 7 | 11 | 20 | 24 | 13
20 | User flow diagrams | Ziyaad | 4 | 7 | 11 | 27 | 31 | 20
21 | Develop Prototype | Keval | 2 | 11 | 13 | 26 | 28 | 15
22 | Research app schemes and style | Ziyaad | 4 | 11 | 15 | 24 | 28 | 13
23 | Prototype testing | Kreason | 5 | 13 | 18 | 28 | 33 | 15
24 | Design layout components | Ziyaad | 5 | 15 | 20 | 28 | 33 | 13
25 | Develop reporting styles | Ziyaad | 2 | 20 | 22 | 33 | 35 | 13
26 | Prototype key interactions | Ziyaad | 2 | 11 | 13 | 31 | 33 | 20
27 | Device Compatibility | Kreason | 2 | 13 | 15 | 33 | 35 | 20
28 | Device Compatibility Matrix | Kreason | 2 | 15 | 17 | 35 | 37 | 20
29 | Optimisation | Keval | 2 | 22 | 24 | 35 | 37 | 13
30 | App Start-up Optimisation | Kreason | 2 | 24 | 26 | 37 | 39 | 13
31 | Database deployment | Keval | 8 | 10 | 18 | 25 | 33 | 15
32 | Database Access Control | Kreason | 2 | 19 | 21 | 33 | 35 | 14
33 | Database Migration Workflows | Ziyaad | 2 | 21 | 23 | 35 | 37 | 14
34 | Integrate blob storage | Kreason | 5 | 16 | 19 | 28 | 33 | 14
35 | Set up CI/CD pipeline | Keval | 3 | 14 | 17 | 29 | 32 | 15
36 | Configure CI/CD pipeline | Keval | 4 | 17 | 21 | 32 | 36 | 15
37 | Manage App Store release | Kreason | 3 | 21 | 24 | 36 | 39 | 15
38 | Develop Unit Tests | Keval | 3 | 17 | 20 | 32 | 35 | 15
39 | Implement CI/CD pipelines | Keval | 2 | 20 | 22 | 35 | 37 | 15
40 | Implement Security scans | Kreason | 2 | 22 | 24 | 37 | 39 | 15
41 | User Acceptance Testing | Keval | 3 | 27 | 30 | 39 | 42 | 12
42 | Logging and error tracking | Kreason | 3 | 30 | 33 | 42 | 45 | 12
43 | Analytics and usage metrics | Kreason | 2 | 33 | 35 | 45 | 47 | 12
44 | Short-term post-launch plan | Keval | 4 | 35 | 39 | 47 | 51 | 12